Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story Points)

| Date | 19 July 2026 |
| --- | --- |
| Team ID | ________________________ |
| Project Name | DocBook — Doctor Appointment Booking System (MERN) |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Use the below template to create product backlog and sprint schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Authentication | USN-1 | As a user, I can register as a patient or doctor by entering my name, email, and password. | 3 | High | Backend Dev |
| Sprint-1 |  | USN-2 | As a user, I can log in with my email and password and receive a JWT session token. | 2 | High | Backend Dev |
| Sprint-1 | Doctor Directory | USN-3 | As a patient, I can browse the list of active doctors. | 3 | High | Frontend Dev |
| Sprint-1 |  | USN-4 | As a patient, I can filter or search doctors by specialty or name. | 2 | Medium | Frontend Dev |
| Sprint-2 | Appointment Booking | USN-5 | As a patient, I can view a doctor's profile and live slot availability for a chosen date. | 3 | High | Full-Stack Dev |
| Sprint-2 |  | USN-6 | As a patient, I can book an appointment by selecting a date, time slot, and reason. | 3 | High | Full-Stack Dev |
| Sprint-2 |  | USN-7 | As a patient, I can view all my upcoming and past appointments. | 2 | High | Frontend Dev |
| Sprint-2 |  | USN-8 | As a patient, I can cancel an appointment I no longer need. | 2 | Medium | Frontend Dev |
| Sprint-3 | Doctor Dashboard | USN-9 | As a doctor, I can view the appointments patients have booked with me. | 2 | High | Backend Dev |
| Sprint-3 |  | USN-10 | As a doctor, I can confirm, mark complete, or cancel a booking. | 3 | Medium | Backend Dev |
| Sprint-3 | Admin Management | USN-11 | As an admin, I can add or remove doctors from the public directory. | 3 | High | Full-Stack Dev |
| Sprint-3 |  | USN-12 | As an admin, I can view every appointment booked across the system. | 2 | Medium | Full-Stack Dev |

Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 10 | 6 Days | 01 Jun 2026 | 06 Jun 2026 | 10 | 06 Jun 2026 |
| Sprint-2 | 10 | 6 Days | 08 Jun 2026 | 13 Jun 2026 | 10 | 13 Jun 2026 |
| Sprint-3 | 10 | 6 Days | 15 Jun 2026 | 20 Jun 2026 | 10 | 20 Jun 2026 |

Velocity:

Velocity = Total Story Points Completed / Number of Sprints

Total Story Points = 10 + 10 + 10 = 30

Number of Sprints = 3

Velocity = 30 / 3 = 10

The team's velocity for the DocBook project is 10 Story Points per Sprint.

Burndown Chart:

A burndown chart tracks remaining work against time for a sprint, giving the team a quick visual read on whether they're on pace to finish. It applies to any project with measurable progress over time, not just Scrum teams.

Scrum Burndown Chart — Visual Paradigm

Burndown Charts — Atlassian

Reference:

Agile Project Management — Atlassian

Epics — Atlassian

Sprints — Atlassian

Estimation — Atlassian